## Slide 1: Developing a project budget and a financial plan
Uzhgorod & Satu Mare (6th & 7th July 2017)

## Slide 2: Why is a budget needed?

## Slide 3
Purpose of the project budget
Project planning
Project assessment
Project implementation
Estimate of the resources needed to implement the planned activities
Assessment of the cost-efficiency of the project taking into account the proposed activities and compared to the other projects
Guide for spending/ possible modifications
Basis for the agreement among the partners
Basis for the project monitoring (internal and by the MA)
Basis for the calculation of the financing you need from the programme and your own co-financing
Assessment of how realistic is project implementation

## Slide 4
Budget and the financial plan
Budget
Financial plan
what expenditure and income is foreseen and what are the sources of information to be used for it
when money will flow in and when it will be spent => project cash-flow (payment & receipts)
It is required that the projects provide two-fold financial information on the project in the application
Additional information may be required to assess the financial capacity of the partners

## Slide 5: How should the budget be developed?

## Slide 6
Budget development
Base on the planned project activities
=> divide them into the cost items necessary for the implementation of the activities
Gather information from all partners
=> keep in mind that costs for the same item/ service may vary from country to country
Base your cost estimates on the real costs
=> if necessary, make a market/ price research to establish realistic unit costs
Define the necessary costs
=> do not forget the human resources that need to be involved!

## Slide 7
Budget development
Information dissemination
Expenditure verification (UA)
Coordination
Participation in programme events
Communication activities
Project evaluation
Project visibility
Do not forget to include into the project budget the following costs that might also be needed for the implementation of the project!
Notes: This slide should be adjusted in line with the programme requirements, e.g. for some programmes expenditure verification can be for free

## Slide 8: Practical task: activity-based project planning
Notes: Depending on the available time and size of the group, the task can be executed either in pairs (giving a possibility for a short discussion) or in groups (e.g. among the participants seated around a cabaret style table). Depending on the priorities supported by the programme, the task can be adjusted if needed.

## Slide 9
Important!
Please take into account:
Only costs indicated in the project budget will be eligible during project implementation
Costs need to be reasonable and necessary for the project implementation
Expenditures will need to be backed up with the documents according to the national legislation
Check if there are limitations to the minimum/ maximum project budget in the programme!

## Slide 10
Important!
When putting together the project budget:
Be realistic!
  Do not overestimate, as during the assessment your project budget will be compared to the others
  Do not underestimate, as in case of the project approval you will need to deliver promised project results with the proposed budget
Be cost effective!
  Comply with the requirements of sound financial management, in particular, regarding economy and efficiency
Do not forget that you will need to co-finance the project!

## Slide 11
EU financing
Co-financing of the participating countries
Co-financing of the project partners
Total income
Income
Notes: Co-financing of the participating countries might be there or not, for some programmes it is included into the programme financing (in this case the presenting expert can modify the presentation accordingly).
It is important to stress here that the project partners will need to provide their own co-financing to the project, and this has to be taken into account when making the financial plan of the project, as well as when assessing their own financial capacity to implement the project.

## Slide 12
Expenditure and income
Expenditure
Staff costs
Travel and subsistence costs
Income
EU contribution
Contribution from third parties (e.g. state budget)
Equipment and supplies
Infrastructure and works
Sub-contracted services
Other costs
Revenues (e.g. registration fees)
Interest generated by pre-financing received
Own contribution
Rules on revenues are different in the two programmes
No profit rule during project implementation applies!

## Slide 13: Financial plan: a new requirement for the projects

## Slide 14
Planning project financial flow
Payments
Income put in the time perspective (until end of execution)
Expenditure put in the time perspective (until end of implementation)
Receipts
Based on the occurrence of the project activities during the project implementation
Take into account the major procurements!
Based on the provisions for payment of the grant and state co-financing, as defined in the grant contract
Take into account availability of the own co-financing! … and more!!

## Slide 15
Project financial plan
An indicative overview of the financial flow of the project
Can help project partners to assess their financial capacity to implement the planned project
Tool for allocation of financial resources during the project implementation
This plan has to be REALISTIC!
Notes: Realistic is key here, as the financial plan has to be based on the real situation, not designed in a way that “it looks good on the paper”. It has to be stressed that the plan is indicative, i.e. there should be no close monitoring of its fulfilment, it should rather be viewed by the applicants as a tool for themselves to understand how the cash flow of the project might work.

## Slide 16
When developing the financial plan
Take into account information from all project partners, not just the lead applicant!
Remember that there is a gap in time between submission of the report and transfer of the next pre-financing instalment!
Be ready to provide more than your own co-financing at the moments when the project cash flow is negative
Take into account that the PRE-FINANCING by the partners will be much higher than the CO-FINANCING in certain moments of the execution period
Notes: Realistic is key here, as the financial plan has to be based on the real situation, not designed in a way that “it looks good on the paper”. It has to be stressed that the plan is indicative, i.e. there should be no close monitoring of its fulfilment, it should rather be viewed by the applicants as a tool for themselves to understand how the cash flow of the project might work.

## Slide 17: Good luck with your project budget and financial plan development!