## Slide 1: Building a good work plan
Who, what, when and how
Uzhgorod & Satu Mare (6th & 7th July 2017)

## Slide 2: Project work plan : key elements
Notes: NOTES: here the trainer should explain that during the presentation the basic elements of a project work plan will be detailed

## Slide 3
Project work plan: scope
Scope
What is the most logic and efficient way of organising the partnership’s work in order to deliver the outputs that achieve project objectives and reach the target groups, within schedule and to the desirable quality and quantity levels?
Notes: Note for the trainer: here you should stress that the work plan should take into account : activities, outputs and target value, time and target groups

## Slide 4
Basics of work plan development
Work plan
Consistent
It should be consistent with the outputs given in the project logframe
Transparent
It should provide sufficient information and detail
Logic
It should demonstrate the work flow and how activities build on each other
Concrete and sustainable
It should identify concrete target groups and foresee provisions for sustainability and transferability
Notes: Notes for the trainer:
You should stress the link with the logframe: the work plan/work package is focused on activities designed to achieve outputs which in turn result in the achievement of specific objectives leading to overall objectives.
These are also the elements the assessor will check base on the award criteria of the evaluation grid as explained in the following slide

## Slide 5
Activity and financial : planning be consistent!
Allocate resources
Estimate of the resources needed to implement the planned activities:
Cash flow needs!
You have to calculate the financing you need from the programme and your own co-financing to carry out the planned activities
Project assessment
Don’t forget you’ll need to cover the possible "gaps" in the cash flow (possible gaps in time between submission of the report and transfer of the next pre-financing installment)
The Programme will assess if your project is cost-efficiently designed taking into account the proposed activities and available funds
Do not underestimate, as in case of the project approval you will need to deliver promised project results with the proposed budget
Do not overestimate, both in terms of duration of activities and associated budget
Notes: The work plan also has to take into account the financial plan of the project (and vice versa of course), i.e. that the activities planned are in line with the available financial resources and if the institutions do not have spare resources to "fill in the gaps", probably the activity plan needs to be changed/ adjusted so that they can manage it from the financial perspective as well.

## Slide 6
Evaluation grid criteria: an example
Proposed activities and project outputs are appropriate, practical and consistent with the objectives and expected results?
The time plan is realistic?
The project’s intervention logic clearly presents the proposed activities, results and objectives. The intervention logic and project plan are clear and feasible. The results will improve the situation of the identified target groups and will serve as proper solution for the presented problems and needs. The method of implementing the planned activities is presented in adequate detail.?
Read carefully the criteria of the evaluation grid related to the Project Action plan!
Notes: Note for the trainer : to be adapted for each programme

## Slide 7
Project work plan: key questions
Project work plan defines processes and responsibilities
Who will do what? Which partner is going to take care of which part of the work? How are partners going to work together?
How to plan the work needed to achieve project outputs?
By when ?
Project partners and programme officers will refer to the work plan during the entire period of implementation to see whether the project is on track.
Notes: Notes: the project intervention logic /logframe has already defined the activities and outputs : the work plan will organise them in a logic a consistent process.

## Slide 8
Developing the work Plan: main steps
Step 1: transfer the list of main activities from the Logframe
Step 2: detail further the activities and the related outputs
Step 3: estimate the duration, start and end date of each activity
Step 4: coordinate all activities within the timeline and develop a final schedule
Step 5: identify partners and staff responsible for implementing activities
Notes: Note for the trainer : you can use this slide as a final wrap up

## Slide 9: Work Package approach
Notes: NOTES: here the trainer should introduce how the new ENI CBC programmes are more WP oriented than GANTT oriented in the sense the Timeplan is automaticaly delivered by the online system..

## Slide 10
How detailed should the project work plan be?
Can you manage it?
Avoid breaking down your work plan into too many activities. It is time consuming and will be difficult to monitor during the implementation.
Is your plan clear ?
Avoid statements that are too vague; they will prevent the partners from having a clear understanding of what it is expected of them, and the programme from understanding what you want to do.
Is your plan flexible?
Planning into precise detail what each partner will do for the next 24 or 36 months will almost certainly be inaccurate after just a few week
Use your common sense
Notes: NOTE: HEADINGS ARE WRITTEN IN CAPITALS IN BOLD. THEY ARE CENTRED AND NOT UNDERLINED

## Slide 11
Project time plan: some hints
Administrative procedures are often time-consuming
Check that the number of activities which run in parallel or consequently
Devote appropriate time to promote the final project outputs and results before project end.
Collecting and compare data can be uneven across the regions and time consuming
Plan a soft start to the project because start-up activities will take time
In case of Project investments take into account the delays of public procurement procedures
In the Application form, the overall project time line in a Gantt chart is automatically generated on the basis of information inserted in the work plan
Notes: NOTES: some short inputs to be provided before the group exercises.

## Slide 12: Let’s put it in practice!
Notes: Note for the experts to plan the group exercise : as the programme to which the training is delivered could have its own template, it would be more beneficial for the potential applicants to use the programme template, as they will have to fill it in afterwards. So the trainer shall need to adapt this to the requirements of the particular programme.