## Slide 1: Session 2.1: Developing CBC project ideas
Introduction to problem, stakeholder and objective analyses
Uzhgorod & Satu Mare (6th & 7th July 2017)

## Slide 2
Scope
Time
Budget
Time
Within a given period
Scope
In order to achieve predefined goals
Budget/Cost
Implemented with limited resources
  Combination of planned activities
Risk & Quality

## Slide 3
Inception Phase
Planning Phase
Implementation Phase
Controlling Phase
Closing Phase
PMI MODEL

## Slide 4
Identification of Project Ideas
Analysis of the Project Idea
Planning / Proposal
Financing
Implementation
Monitoring
Project Cycle Management

## Slide 5
Developing a Logical Framework Matrix – assessing consistency among different components of the Project, risks / assumptions and define objectively verifiable performance indicators
Activity Planning – define activities, time / scope / who / when / what / how
Resource Planning – human resources and budget
Problem Analysis – Identification of important problems and causal relationship among all problems
Stakeholder Analysis – Identification of all the stakeholders of the project
Objective Analysis – Provide solutions to the defined problems of the project
Strategy Analysis – develop strategies to tackle the problems identified
Planning
Analysis
Logical Framework Approach

## Slide 6: What do you want to improve? Which is the change you want to get?

## Slide 7
WHAT ARE THE PROBLEMS?
  Problem analysis is the initial stage of project identification: your project will adress a common problem (e.g. cross-border pollution) or a missed opportunity (e.g. limited access to external markets), the situation should be improved at the end of the project as compared to before!
  Check that the problem has a cross-border dimension related to the programme priorities!
It is not enough to state there is a problem, you should analyse its causes and related effects
  Describe first the negative situation and do not start straight away finding the solution to the problem, there are usually several ways to solve a problem!
  You need to get an overview of all causes of the problem, though you will only target some of them in your project (other may need to be included in project external risks and assumptions)
Problem analysis

## Slide 8
Problem analysis: building the problem “tree”
CAUSES
EFFECTS

## Slide 9: Who’s affected by the negative situation?

## Slide 10
Stakeholder analysis
WHOSE PROBLEM IS IT?
Analyse who’s affected - directly or indirectly – by the problem or have an interest in it: individuals, groups of people, institutions or firms (local authorities, environment agency, farmers…) = stakeholders
  Check cross-border dimension: are there stakeholders in several countries of the Black Sea Basin?
  Analyse the impact of the problem on various stakeholders: different groups have different concerns, capacities and interests (sometimes conflicting) - these need to be understood and recognized in the process of problem identification
  Consult stakeholders from the beginning and throughout project design!

## Slide 11: What could be the improved situation?

## Slide 12
Objective analysis
WHAT ARE THE OBJECTIVES?
  Negative situations of the problem tree converted into positive achievements = objectives
  Methodological approach to:
  Get an overview of the desired future situation (when all problems are remedied)
  Illustrate means-ends relationship
  Keep the analysis of potential objectives clearly based on adressing a range of identified priority problems
  Provides the basis for the project strategy analysis!

## Slide 13
Objective analysis: building the “objective tree”
MEANS
ENDS

## Slide 14: What change can you bring under ENI CBC?

## Slide 15
Strategy analysis
DEFINING THE SCOPE OF YOUR PROJECT IDEA
  Shall all identified problems/objectives be tackled or only a few?
What objective(s) cannot be reached acting only on a national/regional/local level and needs CBC?
  What can realistically be afforded within the Black Sea Basin call financial limits?
  Will it contribute to programme indicators?
  How does it build upon previous/current/planned actions in this field? Possible complementarities/synergies/overlaps? Scope for replication?

## Slide 16: Let’s practice on problem and objective analysis

## Slide 17
Problem analysis – Work group per priority
Brainstorm main cross border problems related to the priority and select one individual focal problem – write on yellow card
Identify related problems to this focal problem – write on yellow cards
Establish hierarchy of causes and effects – stick accordingly the cards on the flipchart paper and draw arrows from causes to effects
Identify who’s affected by each problem – write on pink cards and stick next to each related problem
  Think about existing problems, not future or imagined ones!
  The position of the problem in the hierarchy does not indicate its importance!
  A problem is not the absence of a solution, but a negative situation (e.g. “crops are infested with pests” is a problem, “no pesticides are available” is not)!

## Slide 18
Objective analysis – Work group per priority
Reformulate all negative situations of the problems analysis into positive situations that are desirable and realistically achievable – write on green cards
Organise on the flipchart paper accordingly at the same line as appropriate problem
Check the means-ends relationships to ensure validity and completeness of the hierarchy: if necessary revise statements, add new objectives (means) if relevant to achieve the objective at the next higher level, delete objectives which do not seem suitable or necessary
  Assess impact on stakeholders (positive-negative, involvement realistic?) - write on pink cards and stick next to the related objective
  Check complementarities with other relevant initiatives in the same field (e.g. national/regional policies, other EU funded programmes…) – write on blue cards and stick next to the related objective

## Slide 19: Session 2.2: Building an ENI CBC project
Fitting you CBC project idea into an ENI CBC project framework
Uzhgorod & Satu Mare (6th & 7th July 2017)

## Slide 20
What do you want to improve through your CBC project?
What will you do?
Who do you do the project with? How to work in partnership?
Who do you do the project for? Who do you consult and involve?
What can you do when you’ve answered these questions?
Let’s practice with your CBC project idea!

## Slide 21
Aiming at a positive change
Outputs
Results
Impact
PROJECT
Situation
Change
Activities

## Slide 22
Setting project objectives in a logical way
High levels of solid waste dumped into the river
River water quality is deteriorating
No public information or education programs available
Population not aware of the danger of waste dumping
Public information/ education programs established
Population more aware of the danger of waste dumping
The quantity of solid waste dumped into the river is reduced
River water quality is improved
PROBLEMS
OBJECTIVES
PROJECT INTERVENTION LOGIC LEVELS
Broader long-term change to which the project contributes
Linked to a programme priority
What the project aims to achieve
Direct short-term and medium-term effects of the outputs
Tends to focus on changes in behaviour resulting from the outputs
Services, goods, infrastructure that are produced/delivered by the project activities
Impact
Result
Intermediary result
Output

## Slide 23
Strategy analysis: what can you achieve?
DEFINING THE SCOPE OF YOUR CBC PROJECT OBJECTIVES
  Shall all identified problems/objectives be tackled or only a few?
What objective(s) cannot be reached acting only on a national/regional/local level and needs CBC?
  Will it contribute to CBC programme priorities?
  How does it build upon previous/current/planned actions in this field? Possible complementarities/synergies/overlaps? Scope for replication?

## Slide 24: What will you do?

## Slide 25
Defining activities to produce outputs & achieve results
1
1.1
1.1.1
1.1.2
1.2
1.2.1
Result
Outputs
Activities
1.1.3
1.2.2

## Slide 26
Strategy analysis: what needs to be done and how?
DEFINING THE SCOPE OF YOUR CBC PROJECT ACTIVITIES
  Do they take into account programme cross-cutting issues (e.g. gender)?
  What can realistically be afforded within the call financial limits?
  Will the activities produce project outputs that are sustainable?
  What about communication and management/ coordination ?
Are they eligible under the CBC programme rules?

## Slide 27: Who do you do the project for? Who do you consult and involve?

## Slide 28
Who are the stakeholders, beneficiaries, target groups?
TARGET GROUPS
Who will benefit directly from the outputs and result(s) of the project (e.g. population living on the riverside, tourists…)
Those directly involved in the activities (e.g. schools, journalists, tourism agencies…)
FINAL BENEFICIARIES
Who will benefit indirectly or in the long term from the project (e.g. consumers of fish products…)
activities
outputs
results
impact
STAKEHOLDERS
Persons or organisations that can affect or be affected (positively/negatively) by the project (e.g. local authorities, environmental protection agency, industry, other donors…)

## Slide 29
Stakeholders analysis
Stakeholders
Who will benefit?
Who will loose out?
Directly (target groups)
Indirectly/in the long term (final beneficiaries)
What is their capacity and motivation to bring a change?
What are possible actions to address their needs and interest?
Gender relevance?

## Slide 30: Let’s practice with your CBC project idea!

## Slide 31
Develop your project intervention logic!
    Draw your project intervention logic:
      Define the impact level (check programme priorities – what will you contribute to?)
      Define the result level (what do you want to improve, which positive change, who will benefit?)
      Define the output level (what services, goods, infrastructure do you need to achieve the result(s)?)
      Define a few key activities for each output (what will you do to produce/deliver the output?)
Impact
Result 1
Output 1.1
Output 1.3
Output 1.2
Activity 1.1.1
Activity 1.1.2
Activity 1.1.3
Activity 1.2.1
Activity 1.2.2
Activity 1.3.1
Activity 1.3.2
Step 1
Step 3
Step 4
Step 2

## Slide 32: Now let’s consider what can go wrong? On top of financing, what is needed so that the project achieves the positive change?

## Slide 33
What are the assumptions & risks?
    What factors outside the project management control may prevent the project from delivering its outputs, achieving its result(s) and some impact?
 | Assumptions
Impact | 
Result(s) | What key assumption(s) should hold true so that the result(s) contribute to the impact?
Outputs | What key assumption(s) should hold true so that the outputs achieve the result(s)?
Activities | What key assumption(s) should hold true so that the activities produce the outputs?